## Function List Import
function_code | name | description | type | phase | owner | status | module | priority | scope_class | complexity | pd_ba | pd_ux | pd_fe | pd_be | pd_int_data | pd_qa | pd_devops | pd_total | performance_class | target_option_a | target_option_b | target_option_c | performance_note | price_thb | commercial_note
F001 | Sync Item Master: RM / Ingredient / FG / SKU / Barcode |  | Functional |  |  | Draft | Master Data & MMS Integration | Must | Core | High | 5 | 2 | 5 | 10 | 10 | 5 | 2 | 39 | Batch / Async | เริ่ม job ≤5s; งาน 10k rows ≤5m | เริ่ม job ≤3s; งาน 10k rows ≤3m | เริ่ม job ≤3s; งาน 10k rows ≤2m | External system latency ไม่รวม; ต้องมี job status, retry และ error report | 32000 | Allocated proportionally from original role-effort estimate; application scope only
F002 | Sync Standard/Average Cost และแสดง Ex-VAT |  | Functional |  |  | Draft | Master Data & MMS Integration | Must | Core | High | 4 | 1 | 3 | 8 | 8 | 4 | 1 | 29 | Batch / Async | เริ่ม job ≤5s; งาน 10k rows ≤5m | เริ่ม job ≤3s; งาน 10k rows ≤3m | เริ่ม job ≤3s; งาน 10k rows ≤2m | External system latency ไม่รวม; ต้องมี job status, retry และ error report | 24000 | Allocated proportionally from original role-effort estimate; application scope only
F003 | Store/Branch, Department, Ranging, Reason Code, Approval Rule |  | Functional |  |  | Draft | Master Data & MMS Integration | Must | Core | Medium | 5 | 2 | 6 | 8 | 4 | 5 | 1 | 31 | Batch / Async | เริ่ม job ≤5s; งาน 10k rows ≤5m | เริ่ม job ≤3s; งาน 10k rows ≤3m | เริ่ม job ≤3s; งาน 10k rows ≤2m | External system latency ไม่รวม; ต้องมี job status, retry และ error report | 25000 | Allocated proportionally from original role-effort estimate; application scope only
F004 | Scheduled Sync / Manual Upload / Error Reprocess / Sync Log |  | Functional |  |  | Draft | Master Data & MMS Integration | Must | Core | High | 5 | 2 | 5 | 10 | 12 | 6 | 3 | 43 | Batch / Async | เริ่ม job ≤5s; งาน 10k rows ≤5m | เริ่ม job ≤3s; งาน 10k rows ≤3m | เริ่ม job ≤3s; งาน 10k rows ≤2m | External system latency ไม่รวม; ต้องมี job status, retry และ error report | 35000 | Allocated proportionally from original role-effort estimate; application scope only
F005 | Shelf Life, Lot, FIFO/FEFO basic master support |  | Functional |  |  | Draft | Master Data & MMS Integration | Should | Core/Overlap | High | 4 | 2 | 5 | 8 | 5 | 5 | 1 | 30 | Batch / Async | เริ่ม job ≤5s; งาน 10k rows ≤5m | เริ่ม job ≤3s; งาน 10k rows ≤3m | เริ่ม job ≤3s; งาน 10k rows ≤2m | External system latency ไม่รวม; ต้องมี job status, retry และ error report | 24000 | Allocated proportionally from original role-effort estimate; application scope only
F006 | UOM Conversion: Pack/Bag → Gram/Piece พร้อม Base Unit |  | Functional |  |  | Draft | RM to Ingredient Conversion | Must | Core | High | 6 | 3 | 7 | 12 | 3 | 7 | 1 | 39 | Calculation / CRUD | CRUD ≤3s; calculate ≤5s | CRUD ≤2s; calculate ≤3s | CRUD ≤2s; calculate ≤3s | BOM ปกติ 10–30 components; bulk recalculation ใช้ background job | 31000 | Allocated proportionally from original role-effort estimate; application scope only
F007 | Parent/Child Barcode mapping และ stock transaction |  | Functional |  |  | Draft | RM to Ingredient Conversion | Must | Core | High | 5 | 2 | 6 | 12 | 4 | 7 | 1 | 37 | Transactional | Preview ≤5s; confirm ≤5s | Preview ≤3s; confirm ≤4s | Preview ≤3s; confirm ≤3s | Stock confirmation ต้อง atomic; p95 ไม่รวม external sync | 29000 | Allocated proportionally from original role-effort estimate; application scope only
F008 | Yield/Loss conversion และ audit log |  | Functional |  |  | Draft | RM to Ingredient Conversion | Must | Core | High | 5 | 2 | 5 | 10 | 2 | 6 | 1 | 31 | Calculation / CRUD | CRUD ≤3s; calculate ≤5s | CRUD ≤2s; calculate ≤3s | CRUD ≤2s; calculate ≤3s | BOM ปกติ 10–30 components; bulk recalculation ใช้ background job | 24000 | Allocated proportionally from original role-effort estimate; application scope only
F009 | Substitute master priority P1–P3 |  | Functional |  |  | Draft | RM to Ingredient Conversion | Must | Core | Medium | 4 | 2 | 5 | 8 | 1 | 5 | 1 | 26 | Calculation / CRUD | CRUD ≤3s; calculate ≤5s | CRUD ≤2s; calculate ≤3s | CRUD ≤2s; calculate ≤3s | BOM ปกติ 10–30 components; bulk recalculation ใช้ background job | 20000 | Allocated proportionally from original role-effort estimate; application scope only
F010 | Create/Edit/Search/Copy Recipe และ 1 Primary Recipe per FG |  | Functional |  |  | Draft | Recipe & BOM | Must | Core | High | 8 | 5 | 12 | 18 | 2 | 10 | 1 | 56 | Calculation / CRUD | CRUD ≤3s; calculate ≤5s | CRUD ≤2s; calculate ≤3s | CRUD ≤2s; calculate ≤3s | BOM ปกติ 10–30 components; bulk recalculation ใช้ background job | 44000 | Allocated proportionally from original role-effort estimate; application scope only
F011 | รองรับ BOM 5 Types |  | Functional |  |  | Draft | Recipe & BOM | Must | Core | Very High | 10 | 6 | 16 | 28 | 5 | 16 | 2 | 83 | Calculation / CRUD | CRUD ≤3s; calculate ≤5s | CRUD ≤2s; calculate ≤3s | CRUD ≤2s; calculate ≤3s | BOM ปกติ 10–30 components; bulk recalculation ใช้ background job | 71000 | Allocated proportionally from original role-effort estimate; application scope only
F012 | Cost, GP, Packaging Cost, Min Batch, Yield/Loss calculation |  | Functional |  |  | Draft | Recipe & BOM | Must | Core | Very High | 8 | 4 | 10 | 24 | 4 | 14 | 1 | 65 | Calculation / CRUD | CRUD ≤3s; calculate ≤5s | CRUD ≤2s; calculate ≤3s | CRUD ≤2s; calculate ≤3s | BOM ปกติ 10–30 components; bulk recalculation ใช้ background job | 51000 | Allocated proportionally from original role-effort estimate; application scope only
F013 | Recipe Workflow Draft → Approval → Active → Inactive |  | Functional |  |  | Draft | Recipe & BOM | Must | Core | High | 6 | 4 | 8 | 14 | 2 | 9 | 1 | 44 | Calculation / CRUD | CRUD ≤3s; calculate ≤5s | CRUD ≤2s; calculate ≤3s | CRUD ≤2s; calculate ≤3s | BOM ปกติ 10–30 components; bulk recalculation ใช้ background job | 34000 | Allocated proportionally from original role-effort estimate; application scope only
F014 | Version History, Audit Trail, Creator/Approver |  | Functional |  |  | Draft | Recipe & BOM | Must | Core | High | 5 | 3 | 6 | 12 | 1 | 7 | 1 | 35 | Calculation / CRUD | CRUD ≤3s; calculate ≤5s | CRUD ≤2s; calculate ≤3s | CRUD ≤2s; calculate ≤3s | BOM ปกติ 10–30 components; bulk recalculation ใช้ background job | 27000 | Allocated proportionally from original role-effort estimate; application scope only
F015 | Bulk search สูตรที่ใช้วัตถุดิบเดียวกันและ Bulk Update |  | Functional |  |  | Draft | Recipe & BOM | Should | Core | High | 5 | 3 | 8 | 14 | 2 | 8 | 1 | 41 | Calculation / CRUD | CRUD ≤3s; calculate ≤5s | CRUD ≤2s; calculate ≤3s | CRUD ≤2s; calculate ≤3s | BOM ปกติ 10–30 components; bulk recalculation ใช้ background job | 32000 | Allocated proportionally from original role-effort estimate; application scope only
F016 | Store Mapping / Ranging per Recipe |  | Functional |  |  | Draft | Recipe & BOM | Must | Core | Medium | 4 | 2 | 5 | 8 | 2 | 5 | 1 | 27 | Calculation / CRUD | CRUD ≤3s; calculate ≤5s | CRUD ≤2s; calculate ≤3s | CRUD ≤2s; calculate ≤3s | BOM ปกติ 10–30 components; bulk recalculation ใช้ background job | 21000 | Allocated proportionally from original role-effort estimate; application scope only
F017 | Simulation workspace ไม่กระทบสูตรจริง |  | Functional |  |  | Draft | R&D Simulation | Must | Core | High | 7 | 5 | 10 | 16 | 2 | 9 | 1 | 50 | Calculation / CRUD | CRUD ≤3s; calculate ≤5s | CRUD ≤2s; calculate ≤3s | CRUD ≤2s; calculate ≤3s | BOM ปกติ 10–30 components; bulk recalculation ใช้ background job | 39000 | Allocated proportionally from original role-effort estimate; application scope only
F018 | คำนวณ Selling Price ↔ Target GP |  | Functional |  |  | Draft | R&D Simulation | Must | Core | High | 5 | 3 | 6 | 12 | 1 | 7 | 1 | 35 | Calculation / CRUD | CRUD ≤3s; calculate ≤5s | CRUD ≤2s; calculate ≤3s | CRUD ≤2s; calculate ≤3s | BOM ปกติ 10–30 components; bulk recalculation ใช้ background job | 27000 | Allocated proportionally from original role-effort estimate; application scope only
F019 | Copy Simulation to Recipe + Approval Notification |  | Functional |  |  | Draft | R&D Simulation | Must | Core | Medium | 4 | 3 | 5 | 8 | 1 | 5 | 1 | 27 | Calculation / CRUD | CRUD ≤3s; calculate ≤5s | CRUD ≤2s; calculate ≤3s | CRUD ≤2s; calculate ≤3s | BOM ปกติ 10–30 components; bulk recalculation ใช้ background job | 21000 | Allocated proportionally from original role-effort estimate; application scope only
F020 | Monthly / Weekly / Daily Plan |  | Functional |  |  | Draft | Production Planning | Must | Core | Very High | 10 | 6 | 16 | 24 | 4 | 15 | 2 | 77 | Complex Calculation | 100 FG ≤10s; 500 FG ≤60s | 500 FG ≤30s; 2k FG ≤3m | 2k FG ≤45s; 10k FG ≤5m | วัดหลังข้อมูล Forecast พร้อมแล้ว; nested BOM เฉลี่ยไม่เกิน 3 ระดับ | 60000 | Allocated proportionally from original role-effort estimate; application scope only
F021 | Import AI Forecast และแสดง 7/30 วัน |  | Functional |  |  | Draft | Production Planning | Must | Core | High | 5 | 3 | 8 | 10 | 10 | 7 | 2 | 45 | Batch / Async | เริ่ม job ≤5s; งาน 10k rows ≤5m | เริ่ม job ≤3s; งาน 10k rows ≤3m | เริ่ม job ≤3s; งาน 10k rows ≤2m | External system latency ไม่รวม; ต้องมี job status, retry และ error report | 36000 | Allocated proportionally from original role-effort estimate; application scope only
F022 | Stock availability, Shortage Alert, Substitute selection |  | Functional |  |  | Draft | Production Planning | Must | Core | Very High | 8 | 4 | 12 | 22 | 5 | 13 | 2 | 66 | Complex Calculation | 100 FG ≤10s; 500 FG ≤60s | 500 FG ≤30s; 2k FG ≤3m | 2k FG ≤45s; 10k FG ≤5m | วัดหลังข้อมูล Forecast พร้อมแล้ว; nested BOM เฉลี่ยไม่เกิน 3 ระดับ | 52000 | Allocated proportionally from original role-effort estimate; application scope only
F023 | Promotion/Ranging/New item flag และ Export Plan |  | Functional |  |  | Draft | Production Planning | Should | Core/Overlap | High | 6 | 4 | 10 | 14 | 3 | 9 | 1 | 47 | Batch / Async | เริ่ม job ≤5s; งาน 10k rows ≤5m | เริ่ม job ≤3s; งาน 10k rows ≤3m | เริ่ม job ≤3s; งาน 10k rows ≤2m | External system latency ไม่รวม; ต้องมี job status, retry และ error report | 37000 | Allocated proportionally from original role-effort estimate; application scope only
F024 | Plan Approval Workflow |  | Functional |  |  | Draft | Production Planning | Must | Core | Medium | 4 | 3 | 5 | 8 | 1 | 5 | 1 | 27 | Complex Calculation | 100 FG ≤10s; 500 FG ≤60s | 500 FG ≤30s; 2k FG ≤3m | 2k FG ≤45s; 10k FG ≤5m | วัดหลังข้อมูล Forecast พร้อมแล้ว; nested BOM เฉลี่ยไม่เกิน 3 ระดับ | 21000 | Allocated proportionally from original role-effort estimate; application scope only
F025 | สร้างใบเบิกจากแผน / Manual / Additional Requisition |  | Functional |  |  | Draft | Material Requisition | Must | Core | High | 7 | 4 | 10 | 16 | 2 | 10 | 1 | 50 | Transactional | Preview ≤5s; confirm ≤5s | Preview ≤3s; confirm ≤4s | Preview ≤3s; confirm ≤3s | Stock confirmation ต้อง atomic; p95 ไม่รวม external sync | 39000 | Allocated proportionally from original role-effort estimate; application scope only
F026 | Approval, Reject, Issued, Completed/Closed |  | Functional |  |  | Draft | Material Requisition | Must | Core | High | 6 | 4 | 8 | 14 | 2 | 9 | 1 | 44 | Transactional | Preview ≤5s; confirm ≤5s | Preview ≤3s; confirm ≤4s | Preview ≤3s; confirm ≤3s | Stock confirmation ต้อง atomic; p95 ไม่รวม external sync | 34000 | Allocated proportionally from original role-effort estimate; application scope only
F027 | Stock check, Transfer/Adjust by Reason Code |  | Functional |  |  | Draft | Material Requisition | Must | Core | High | 6 | 3 | 7 | 16 | 4 | 10 | 1 | 47 | Transactional | Preview ≤5s; confirm ≤5s | Preview ≤3s; confirm ≤4s | Preview ≤3s; confirm ≤3s | Stock confirmation ต้อง atomic; p95 ไม่รวม external sync | 37000 | Allocated proportionally from original role-effort estimate; application scope only
F028 | Print A4 Requisition Slip + Reconcile Plan/Issue/Actual |  | Functional |  |  | Draft | Material Requisition | Should | Core | Medium | 4 | 3 | 6 | 8 | 2 | 5 | 1 | 29 | Transactional | Preview ≤5s; confirm ≤5s | Preview ≤3s; confirm ≤4s | Preview ≤3s; confirm ≤3s | Stock confirmation ต้อง atomic; p95 ไม่รวม external sync | 23000 | Allocated proportionally from original role-effort estimate; application scope only
F029 | บันทึกยอดผลิตหลายรอบระหว่างวัน |  | Functional |  |  | Draft | Production Execution | Must | Core | High | 6 | 4 | 10 | 16 | 2 | 10 | 1 | 49 | Transactional | Preview ≤5s; confirm ≤5s | Preview ≤3s; confirm ≤4s | Preview ≤3s; confirm ≤3s | Stock confirmation ต้อง atomic; p95 ไม่รวม external sync | 38000 | Allocated proportionally from original role-effort estimate; application scope only
F030 | ตัด Ingredient/Packaging ทันทีตาม BOM |  | Functional |  |  | Draft | Production Execution | Must | Core | Very High | 8 | 3 | 8 | 24 | 5 | 14 | 2 | 64 | Transactional | Preview ≤5s; confirm ≤5s | Preview ≤3s; confirm ≤4s | Preview ≤3s; confirm ≤3s | Stock confirmation ต้อง atomic; p95 ไม่รวม external sync | 51000 | Allocated proportionally from original role-effort estimate; application scope only
F031 | ตรวจ Stock ก่อนผลิตและป้องกันผลิตเกิน |  | Functional |  |  | Draft | Production Execution | Must | Core | High | 5 | 2 | 6 | 14 | 3 | 9 | 1 | 40 | Transactional | Preview ≤5s; confirm ≤5s | Preview ≤3s; confirm ≤4s | Preview ≤3s; confirm ≤3s | Stock confirmation ต้อง atomic; p95 ไม่รวม external sync | 32000 | Allocated proportionally from original role-effort estimate; application scope only
F032 | Waste / Tasting / Giveaway + Approval + cutoff time |  | Functional |  |  | Draft | Production Execution | Must | Core | High | 6 | 4 | 9 | 16 | 2 | 10 | 1 | 48 | Transactional | Preview ≤5s; confirm ≤5s | Preview ≤3s; confirm ≤4s | Preview ≤3s; confirm ≤3s | Stock confirmation ต้อง atomic; p95 ไม่รวม external sync | 37000 | Allocated proportionally from original role-effort estimate; application scope only
F033 | ผู้บันทึกและผู้อนุมัติต้องไม่ใช่คนเดียวกัน |  | Functional |  |  | Draft | Production Execution | Must | Core | Medium | 3 | 1 | 3 | 6 | 1 | 4 | 1 | 19 | Transactional | Preview ≤5s; confirm ≤5s | Preview ≤3s; confirm ≤4s | Preview ≤3s; confirm ≤3s | Stock confirmation ต้อง atomic; p95 ไม่รวม external sync | 15000 | Allocated proportionally from original role-effort estimate; application scope only
F034 | RM / Ingredient / FG stock ledger |  | Functional |  |  | Draft | Inventory & EOD | Must | Core | Very High | 8 | 4 | 10 | 26 | 5 | 16 | 2 | 71 | Transactional | Preview ≤5s; confirm ≤5s | Preview ≤3s; confirm ≤4s | Preview ≤3s; confirm ≤3s | Stock confirmation ต้อง atomic; p95 ไม่รวม external sync | 56000 | Allocated proportionally from original role-effort estimate; application scope only
F035 | Weighted Average Cost ตาม Ingredient/Substitute จริง |  | Functional |  |  | Draft | Inventory & EOD | Must | Core | Very High | 8 | 2 | 6 | 24 | 5 | 15 | 1 | 61 | Transactional | Preview ≤5s; confirm ≤5s | Preview ≤3s; confirm ≤4s | Preview ≤3s; confirm ≤3s | Stock confirmation ต้อง atomic; p95 ไม่รวม external sync | 48000 | Allocated proportionally from original role-effort estimate; application scope only
F036 | EOD Reconcile: Production − Sales − Waste − Tasting |  | Functional |  |  | Draft | Inventory & EOD | Must | Core | Very High | 8 | 4 | 10 | 24 | 8 | 15 | 2 | 71 | Transactional | Preview ≤5s; confirm ≤5s | Preview ≤3s; confirm ≤4s | Preview ≤3s; confirm ≤3s | Stock confirmation ต้อง atomic; p95 ไม่รวม external sync | 56000 | Allocated proportionally from original role-effort estimate; application scope only
F037 | Generate Stock Adjustment และ Sync กลับ MMS/RMS |  | Functional |  |  | Draft | Inventory & EOD | Must | Core | Very High | 7 | 3 | 6 | 18 | 14 | 12 | 3 | 63 | Batch / Async | เริ่ม job ≤5s; งาน 10k rows ≤5m | เริ่ม job ≤3s; งาน 10k rows ≤3m | เริ่ม job ≤3s; งาน 10k rows ≤2m | External system latency ไม่รวม; ต้องมี job status, retry และ error report | 51000 | Allocated proportionally from original role-effort estimate; application scope only
F038 | Multiple daily sync rounds + reprocess/error handling |  | Functional |  |  | Draft | Inventory & EOD | Must | Core | High | 5 | 2 | 5 | 12 | 12 | 8 | 3 | 47 | Batch / Async | เริ่ม job ≤5s; งาน 10k rows ≤5m | เริ่ม job ≤3s; งาน 10k rows ≤3m | เริ่ม job ≤3s; งาน 10k rows ≤2m | External system latency ไม่รวม; ต้องมี job status, retry และ error report | 38000 | Allocated proportionally from original role-effort estimate; application scope only
F039 | Executive Dashboard: Production/Sales/Cost/Waste |  | Functional |  |  | Draft | Dashboard & Reporting | Must | Core | High | 7 | 6 | 14 | 12 | 8 | 10 | 1 | 58 | Report / Analytics | หน้าจอ ≤10s; export ≤90s | หน้าจอ ≤8s; export ≤60s | หน้าจอ ≤6s; export ≤45s | หน้าจอต้องใช้ pagination/aggregation; large export ทำ background job | 45000 | Allocated proportionally from original role-effort estimate; application scope only
F040 | Core Reports: GP, Cost Variance, Stock/FG Movement, Shrinkage |  | Functional |  |  | Draft | Dashboard & Reporting | Must | Core | Very High | 10 | 5 | 16 | 20 | 12 | 15 | 1 | 79 | Report / Analytics | หน้าจอ ≤10s; export ≤90s | หน้าจอ ≤8s; export ≤60s | หน้าจอ ≤6s; export ≤45s | หน้าจอต้องใช้ pagination/aggregation; large export ทำ background job | 63000 | Allocated proportionally from original role-effort estimate; application scope only
F041 | Planning, Production, RM Short/Plan, Waste/Tasting, BOM Version |  | Functional |  |  | Draft | Dashboard & Reporting | Must | Core | High | 8 | 4 | 14 | 18 | 10 | 12 | 1 | 67 | Complex Calculation | 100 FG ≤10s; 500 FG ≤60s | 500 FG ≤30s; 2k FG ≤3m | 2k FG ≤45s; 10k FG ≤5m | วัดหลังข้อมูล Forecast พร้อมแล้ว; nested BOM เฉลี่ยไม่เกิน 3 ระดับ | 53000 | Allocated proportionally from original role-effort estimate; application scope only
F042 | Filter Store/Item/Date + Excel/CSV/PDF Export |  | Functional |  |  | Draft | Dashboard & Reporting | Must | Core | High | 6 | 4 | 12 | 12 | 4 | 9 | 1 | 48 | Batch / Async | เริ่ม job ≤5s; งาน 10k rows ≤5m | เริ่ม job ≤3s; งาน 10k rows ≤3m | เริ่ม job ≤3s; งาน 10k rows ≤2m | External system latency ไม่รวม; ต้องมี job status, retry และ error report | 37000 | Allocated proportionally from original role-effort estimate; application scope only
F043 | AD SSO / Session / JWT |  | Functional |  |  | Draft | User & Access | Must | Core | High | 4 | 2 | 4 | 10 | 2 | 6 | 3 | 31 | Interactive | p95 ≤3s | p95 ≤2s | p95 ≤2s | ไม่รวม AD/IdP latency; login timeout/retry ต้องกำหนดกับ User | 25000 | Allocated proportionally from original role-effort estimate; application scope only
F044 | RBAC by Role / Department / Store |  | Functional |  |  | Draft | User & Access | Must | Core | High | 6 | 3 | 8 | 14 | 2 | 9 | 2 | 44 | Interactive | p95 ≤3s | p95 ≤2s | p95 ≤2s | ไม่รวม AD/IdP latency; login timeout/retry ต้องกำหนดกับ User | 35000 | Allocated proportionally from original role-effort estimate; application scope only
F045 | User/Department/Store administration |  | Functional |  |  | Draft | User & Access | Must | Core | Medium | 5 | 3 | 8 | 10 | 1 | 6 | 1 | 34 | Interactive | p95 ≤3s | p95 ≤2s | p95 ≤2s | ไม่รวม AD/IdP latency; login timeout/retry ต้องกำหนดกับ User | 27000 | Allocated proportionally from original role-effort estimate; application scope only
F046 | In-app Approval / Shortage / Overdue Notification |  | Functional |  |  | Draft | Notification | Must | Core | Medium | 5 | 3 | 7 | 10 | 2 | 6 | 1 | 34 | Complex Calculation | 100 FG ≤10s; 500 FG ≤60s | 500 FG ≤30s; 2k FG ≤3m | 2k FG ≤45s; 10k FG ≤5m | วัดหลังข้อมูล Forecast พร้อมแล้ว; nested BOM เฉลี่ยไม่เกิน 3 ระดับ | 27000 | Allocated proportionally from original role-effort estimate; application scope only
F047 | HTTPS, validation, SQLi/XSS control, audit logs |  | Functional |  |  | Draft | Security & Audit | Must | Core | High | 4 | 1 | 3 | 12 | 2 | 8 | 4 | 34 | Interactive | p95 ≤3s | p95 ≤2s | p95 ≤2s | ไม่รวม AD/IdP latency; login timeout/retry ต้องกำหนดกับ User | 27000 | Allocated proportionally from original role-effort estimate; application scope only
F048 | MMS Read/Write interface contract and implementation |  | Functional |  |  | Draft | Integration | Must | Core | Very High | 8 | 2 | 4 | 12 | 24 | 12 | 4 | 66 | Batch / Async | เริ่ม job ≤5s; งาน 10k rows ≤5m | เริ่ม job ≤3s; งาน 10k rows ≤3m | เริ่ม job ≤3s; งาน 10k rows ≤2m | External system latency ไม่รวม; ต้องมี job status, retry และ error report | 55000 | Allocated proportionally from original role-effort estimate; application scope only
F049 | POS Sales interface and transaction reconciliation |  | Functional |  |  | Draft | Integration | Must | Core | High | 6 | 2 | 4 | 10 | 18 | 10 | 3 | 53 | Batch / Async | เริ่ม job ≤5s; งาน 10k rows ≤5m | เริ่ม job ≤3s; งาน 10k rows ≤3m | เริ่ม job ≤3s; งาน 10k rows ≤2m | External system latency ไม่รวม; ต้องมี job status, retry และ error report | 44000 | Allocated proportionally from original role-effort estimate; application scope only
F050 | RMS Read/Write cost, FG sales, stock adjustment |  | Functional |  |  | Draft | Integration | Must | Core | Very High | 7 | 2 | 4 | 12 | 22 | 11 | 4 | 62 | Batch / Async | เริ่ม job ≤5s; งาน 10k rows ≤5m | เริ่ม job ≤3s; งาน 10k rows ≤3m | เริ่ม job ≤3s; งาน 10k rows ≤2m | External system latency ไม่รวม; ต้องมี job status, retry และ error report | 51000 | Allocated proportionally from original role-effort estimate; application scope only
F051 | AI Forecast Read interface |  | Functional |  |  | Draft | Integration | Must | Core | Medium | 4 | 1 | 3 | 6 | 10 | 5 | 2 | 31 | Batch / Async | เริ่ม job ≤5s; งาน 10k rows ≤5m | เริ่ม job ≤3s; งาน 10k rows ≤3m | เริ่ม job ≤3s; งาน 10k rows ≤2m | External system latency ไม่รวม; ต้องมี job status, retry และ error report | 26000 | Allocated proportionally from original role-effort estimate; application scope only
F052 | Dev, QA, UAT, Prod configuration and deployment pipeline |  | Functional |  |  | Draft | Platform / Infra | Must | Core | High | 4 | 1 | 2 | 5 | 3 | 4 | 20 | 39 | Operational / NFR | ตาม operation | ตาม operation | ตาม operation | เป็นงาน platform/delivery ไม่ใช่ online user response | 33000 | Allocated proportionally from original role-effort estimate; application scope only
F053 | Monitoring, application/error/audit log, backup configuration |  | Functional |  |  | Draft | Platform / Infra | Must | Core | High | 4 | 1 | 2 | 6 | 2 | 4 | 14 | 33 | Operational / NFR | ตาม operation | ตาม operation | ตาม operation | เป็นงาน platform/delivery ไม่ใช่ online user response | 28000 | Allocated proportionally from original role-effort estimate; application scope only
F054 | System Integration Test, UAT support, performance baseline |  | Functional |  |  | Draft | Testing & Delivery | Must | Core | Very High | 8 | 2 | 4 | 8 | 6 | 35 | 6 | 69 | Batch / Async | เริ่ม job ≤5s; งาน 10k rows ≤5m | เริ่ม job ≤3s; งาน 10k rows ≤3m | เริ่ม job ≤3s; งาน 10k rows ≤2m | External system latency ไม่รวม; ต้องมี job status, retry และ error report | 52000 | Allocated proportionally from original role-effort estimate; application scope only
F055 | Data migration templates / initial master loading |  | Functional |  |  | Draft | Testing & Delivery | Must | Core | High | 6 | 1 | 3 | 6 | 12 | 8 | 2 | 38 | Batch / Async | เริ่ม job ≤5s; งาน 10k rows ≤5m | เริ่ม job ≤3s; งาน 10k rows ≤3m | เริ่ม job ≤3s; งาน 10k rows ≤2m | External system latency ไม่รวม; ต้องมี job status, retry และ error report | 31000 | Allocated proportionally from original role-effort estimate; application scope only
F056 | User manual, admin manual, training, handover |  | Functional |  |  | Draft | Testing & Delivery | Must | Core | Medium | 10 | 3 | 3 | 3 | 1 | 5 | 1 | 26 | Interactive | p95 ≤3s | p95 ≤2s | p95 ≤2s | ไม่รวม AD/IdP latency; login timeout/retry ต้องกำหนดกับ User | 20000 | Allocated proportionally from original role-effort estimate; application scope only
F057 | PM, requirement workshops, design governance, status/reporting |  | Functional |  |  | Draft | Project Governance | Must | Core | High | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | Report / Analytics | หน้าจอ ≤10s; export ≤90s | หน้าจอ ≤8s; export ≤60s | หน้าจอ ≤6s; export ≤45s | หน้าจอต้องใช้ pagination/aggregation; large export ทำ background job | 37000 | Allocated proportionally from original role-effort estimate; application scope only
F058 | Gross Requirement and nested BOM explosion |  | Functional |  |  | Draft | Planning & MRP-Lite | Must | Core | High | 5 | 2 | 5 | 12 | 2 | 7 | 2 | 35 | Complex Calculation | 100 FG ≤10s; 500 FG ≤60s | 500 FG ≤30s; 2k FG ≤3m | 2k FG ≤45s; 10k FG ≤5m | Active approved BOM only; cycle detection required | 28000 | Allocated proportionally from original role-effort estimate; application scope only
F059 | Net Requirement: On-hand / Incoming / Shortage |  | Functional |  |  | Draft | Planning & MRP-Lite | Must | Core/Integration | High | 5 | 2 | 5 | 12 | 6 | 7 | 2 | 39 | Complex Calculation | 100 FG ≤10s; 500 FG ≤60s | 500 FG ≤30s; 2k FG ≤3m | 2k FG ≤45s; 10k FG ≤5m | Official stock and inbound quantities sourced from SAP/MMS | 31000 | Allocated proportionally from original role-effort estimate; application scope only
F060 | Purchase/Transfer Suggestion Export without official PO creation |  | Functional |  |  | Draft | Planning & MRP-Lite | Should | Enhancement-Ready | Medium | 4 | 2 | 5 | 8 | 5 | 5 | 2 | 31 | Batch / Async | เริ่ม job ≤5s; export ≤90s | เริ่ม job ≤3s; export ≤60s | เริ่ม job ≤3s; export ≤45s | Human review required; SAP PR/PO creation excluded | 25000 | Allocated proportionally from original role-effort estimate; application scope only
F061 | Operational Inventory Sub-ledger and SAP reconciliation report |  | Functional |  |  | Draft | ERP Boundary & Reconciliation | Must | Core/Integration | High | 6 | 3 | 6 | 12 | 8 | 8 | 3 | 46 | Report / Analytics | หน้าจอ ≤10s; export ≤90s | หน้าจอ ≤8s; export ≤60s | หน้าจอ ≤6s; export ≤45s | BOM–CFW balance is operational; SAP remains official inventory | 37000 | Allocated proportionally from original role-effort estimate; application scope only
F062 | Opening stock / inbound snapshot import from SAP or MMS |  | Functional |  |  | Draft | ERP Boundary & Reconciliation | Must | Integration | High | 5 | 2 | 5 | 10 | 10 | 7 | 3 | 42 | Batch / Async | 10k rows ≤5m | 10k rows ≤3m | 10k rows ≤2m | Goods Receipt processing remains outside BOM–CFW | 34000 | Allocated proportionally from original role-effort estimate; application scope only
F063 | Month-end reconciliation snapshot; no financial close |  | Functional |  |  | Draft | ERP Boundary & Reconciliation | Should | Boundary | Medium | 4 | 2 | 4 | 8 | 5 | 5 | 2 | 30 | Report / Analytics | หน้าจอ ≤10s; export ≤90s | หน้าจอ ≤8s; export ≤60s | หน้าจอ ≤6s; export ≤45s | SAP owns period lock, valuation, carry forward and official opening balance | 24000 | Allocated proportionally from original role-effort estimate; application scope only
F064 | Personalized My Tasks by user, role, store and department |  | Functional |  |  | Draft | AI-Ready Smart Dashboard | Must | Core | High | 5 | 4 | 8 | 10 | 2 | 7 | 2 | 38 | Interactive / Query | p95 ≤3s | p95 ≤2s | p95 ≤2s | Backend scope filtering is authoritative; no cross-scope leakage | 30000 | Allocated proportionally from original role-effort estimate; application scope only
F065 | Rule-based Alerts from stock, import, workflow and reconciliation data |  | Functional |  |  | Draft | AI-Ready Smart Dashboard | Must | Core | High | 5 | 4 | 8 | 12 | 3 | 8 | 2 | 42 | Interactive / Query | Dashboard ≤3s; refresh ≤15m | Dashboard ≤2s; refresh ≤10m | Dashboard ≤2s; refresh ≤5m | Deterministic rules only; source and threshold must be explainable | 33000 | Allocated proportionally from original role-effort estimate; application scope only
F066 | Recommendations and Improvement cards with next-best action links |  | Functional |  |  | Draft | AI-Ready Smart Dashboard | Must | Core | High | 6 | 5 | 10 | 12 | 2 | 8 | 2 | 45 | Interactive / Query | p95 ≤3s | p95 ≤2s | p95 ≤2s | Template-based wording; no GenAI or autonomous decision | 35000 | Allocated proportionally from original role-effort estimate; application scope only
F067 | Priority scoring, severity, SLA aging and sorting |  | Functional |  |  | Draft | AI-Ready Smart Dashboard | Must | Core | Medium | 4 | 3 | 5 | 8 | 1 | 5 | 1 | 27 | Interactive / Query | p95 ≤3s | p95 ≤2s | p95 ≤2s | Score derived from deterministic business impact and due date | 21000 | Allocated proportionally from original role-effort estimate; application scope only
F068 | Dismiss, Snooze, Resolve and insight action audit |  | Functional |  |  | Draft | AI-Ready Smart Dashboard | Should | Core | Medium | 4 | 3 | 6 | 8 | 1 | 6 | 1 | 29 | Transactional | Action ≤3s | Action ≤2s | Action ≤2s | Insight state changes must be auditable and idempotent | 22000 | Allocated proportionally from original role-effort estimate; application scope only
F069 | Role-specific daily summary using templates |  | Functional |  |  | Draft | AI-Ready Smart Dashboard | Should | Enhancement-Ready | Medium | 4 | 4 | 6 | 8 | 1 | 5 | 1 | 29 | Interactive / Query | p95 ≤3s | p95 ≤2s | p95 ≤2s | Baseline is template-generated text; GenAI narrative is future enhancement | 22000 | Allocated proportionally from original role-effort estimate; application scope only

## README
Import-ready Function List — CFW Project (Estimate/SI type)
Highlighted cells (light yellow) in the data sheet = fields not present in the original source file. Fill in manually before import: description, phase (UR/DR/PU-PT/IFT/BCT/UAT/IP), owner.
status defaulted to 'Draft' and type defaulted to 'Functional' for all 69 rows — adjust as needed.
pd_total will be recalculated automatically by the backend on import (sum of pd_ba..pd_devops) — the value here is kept for reference/cross-check only.
This file's headers match the 'Estimate/SI' project_type schema defined in ClaudeCode_SchemaPatch_ProjectType.md.