## Requirements
ID | Track | Title | Type | Deliverable | Source | Clarification | Assumption | Domains
REQ-T1-001 | T1 | AWS Legacy Zone HLD/LLD | ARCHITECTURE | DESIGN_DOCUMENT | SOW | OPEN | NONE | account structure,network segmentation,security,routing,logging,monitoring,governance
REQ-T1-002 | T1 | AWS Landing Zone / Legacy Zone As-Built | ARCHITECTURE | AS_BUILT | SOW | OPEN | NONE | landing zone,legacy zone,thailand region
REQ-T1-003 | T1 | Core Infrastructure Services Design / As-Built | IDENTITY | DESIGN_AND_AS_BUILT | SOW | OPEN | NONE | active directory,dns,firewall,jump host,cyberark
REQ-T1-004 | T1 | Jump Host Migration | MIGRATION | MIGRATED_SERVERS | SOW | NONE | NONE | jump host
REQ-T1-005 | T1 | CyberArk Migration | MIGRATION | MIGRATED_SERVERS | SOW | NONE | NONE | cyberark
REQ-T1-006 | T1 | Hybrid / Multi-cloud Connectivity Assessment | CONNECTIVITY | ASSESSMENT | SOW | OPEN | NONE | on-premises,direct connect,azure,gcp,hybrid,multi-cloud
REQ-T2-001 | T2 | Migration Factory Design | MIGRATION | DESIGN_DOCUMENT | SOW | OPEN | NONE | staging subnet,routing,vpc endpoint
REQ-T2-002 | T2 | Migration Network Foundation As-Built | NETWORK | AS_BUILT | SOW | NONE | NONE | subnets,route tables,direct connect,privatelink,security groups
REQ-T2-003 | T2 | AWS MGN Agent Enablement / Configuration | MIGRATION | CONFIG_SUMMARY | SOW | NONE | OPEN | dns resolution,endpoint usage,agent installation
REQ-T2-004 | T2 | Pilot Migration Test / Verification | TEST / VERIFICATION | TEST_REPORT | SOW | OPEN | OPEN | private-path migration,health status
REQ-T2-005 | T2 | Migration Runbook / Operational Handover | OPERATIONS | RUNBOOK | SOW | OPEN | NONE | migration waves,migration factory execution