## document_templates_seed
doc_code | doc_name | phase_code | phase_name | doc_set_no | doc_set_name | mandatory_critical | mandatory_non_critical | mandatory_ma | mandatory_rollout | defined_by | documented_by | approved_by
101 | Business Flow | 10 | UR | 01 | Business/ Operation | M | M | M | M | User | User/IT (User)/App Team | User/IS GM
102 | Function List | 10 | UR | 02 | Function List | M | M | O | O | User/IS | IT (User)/App Team | User/IS GM
103 | Function Outline Batch | 10 | UR | 03 | Functional Requirement | M | M | O | O | User | User/IT (User)/App Team | User/IS GM
104 | Function Outline Screen | 10 | UR | 03 | Functional Requirement | M | M | O | O | User | User/IT (User)/App Team | User/IS GM
105 | Function Outline Report | 10 | UR | 03 | Functional Requirement | M | M | O | O | User | User/IT (User)/App Team | User/IS GM
106 | Report List | 10 | UR | 03 | Functional Requirement | M | M | O | O | User | User/IT (User)/App Team | User/IS GM
107 | Function Relation Diagram | 10 | UR | 03 | Functional Requirement | O | O | O | O | User | IT (User)/App Team | User/IS GM
108 | ER Roughly | 10 | UR | 04 | Data | O | O | O | O | User/IS | IT (User)/App Team | User/IS GM
109 | System Relation | 10 | UR | 05 | System Relation | M | M | O | O | User | IT (User)/App Team | User/IS GM
110 | Data Migration UR | 10 | UR | 06 | Data Migration | M | M | O | O | User | IT (User)/App Team | User/IS GM
111 | Performance Requirement | 10 | UR | 07 | Performance Requirement | M | M | O | M | User | User/IT (User)/App Team | User/IS GM
112 | System Requirement | 10 | UR | 08 | System Requirement | M | M | O | M | User | IT (User)/App Team | User/IS GM
201 | UISS Batch | 20 | DR | 01 | UISS Design | M | M | O | O | All parties | App Team | User/IS GM
202 | UISS Screen | 20 | DR | 01 | UISS Design | M | M | O | O | All parties | App Team
203 | UISS Report | 20 | DR | 01 | UISS Design | M | M | O | O | All parties | App Team
204 | ER Complete | 20 | DR | 02 | DB Design and Sizing | M | M | M | M | All parties | App Team
205 | DB Structure | 20 | DR | 02 | DB Design and Sizing | M | M | M | O | All parties | App Team
206 | Logical Storage Sizing | 20 | DR | 02 | DB Design and Sizing | M | M | M | M | All parties | App Team
207 | Interface File Layout | 20 | DR | 03 | System Relation | M | M | O | O | All parties | App Team | User/IS GM
208 | Convert Data | 20 | DR | 04 | Data Migration | M | M | O | O | All parties | App Team
209 | Function Overview | 20 | DR | 05 | Function Overview | M | M | O | O | All parties | App Team
301 | CFW Usage App Config | 30 | DN | 01 | CFW Usage & App Config | M | M | M | M | App Team | App Team | -
302 | Object List | 30 | DN | 02 | Object List | M | M | O | O | App Team | App Team | -
303 | Program Spec | 30 | DN | 03 | Program Spec | M | M | M | O | App Team | App Team | IS Manager
304 | Program Spec | 30 | DN | 03 | Program Spec | M | M | M | O | App Team | App Team
305 | Program Spec | 30 | DN | 03 | Program Spec | M | M | M | O | App Team | App Team
306 | Program Spec | 30 | DN | 03 | Program Spec | M | M | M | O | App Team | App Team
401 | Migration Sheet Blank | 40 | PU | 01 | Data Migration | O | O | O | O | App Team | App Team | -
402 | PT Summary | 40 | PU | 02 | Test Script | O | O | O | O | App Team | App Team | -
403 | PT Script | 40 | PU | 02 | Test Script | O | O | O | O | App Team | App Team | -
404 | Test Result | 40 | PU | 03 | Test Result | O | O | O | O | App Team | App Team | -
405 | Test Result | 40 | PU | 03 | Test Result | O | O | O | O | App Team | App Team | -
501 | IFT Summary | 50 | ST | 02 | Test Script | M | M | O | O | App Team | App Team | -
502 | IFT Script | 50 | ST | 02 | Test Script | M | M | M | O | App Team | App Team | -
503 | Response Test | 50 | ST | 02 | Test Script | M | M | M | M | App Team | App Team | User/IS Manager
504 | Stress Test | 50 | ST | 02 | Test Script | M | O | O | M | IT (User)/App Team | IT (User)/App Team
505 | Irregular Test | 50 | ST | 02 | Test Script | O | O | O | O | App Team | App Team | IS Manager
506 | Break Down Test | 50 | ST | 02 | Test Script | O | O | O | O | App Team | App Team
507 | BCT List | 50 | ST | 02 | Test Script | M | M | O | O | IT (User)/App Team | IT (User)/App Team
508 | BCT Script | 50 | ST | 02 | Test Script | M | M | M | M | IT (User)/App Team | IT (User)/App Team
509 | System Manual | 50 | ST | 05 | System Manual | M | M | M | M | App Team | App Team | User Manager
601 | UT List | 60 | UT | 02 | Test Script | M | M | O | O | IT (User)/User | IT (User)/User
602 | UT Script | 60 | UT | 02 | Test Script | M | M | M | M | IT (User)/User | IT (User)/User
701 | Trial Plan Book | 70 | TR | 01 | Trial | M | M | O | M | IT (User)/User | IT (User)/User | User Manager
801 | Implementation Plan Book | 80 | IP | 01 | Implementation | M | M | O | M | IT (User)/User | IT (User)/User | User/IS Manager
901 | Maintenance | 90 | MA | 01 | Maintenance | M | M | M | M | IT (User)/App Team | App Team

## README
Document Template Master Seed — parsed from 'Deliverible Document List.xlsx' + matched docx filenames
phase_code/phase_name follow the REAL company methodology: UR(10) -> DR(20) -> DN(30) -> PU(40) -> ST(50, covers IFT+BCT+Response/Stress/Irregular/Breakdown test) -> UT(60) -> TR(70, Trial) -> IP(80) -> MA(90).
mandatory_* columns: M = Mandatory, O = Optional, per project category (Critical / Non-Critical / MA / Rollout project).
Import this sheet once into a global 'document_templates' reference table. When a new project is created, auto-populate its 'documents' list by filtering rows where the column matching the project's category = 'M' (Mandatory).
46 unique doc_codes total across all phases.